## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | Prj_Opencart_001
Project Name | OpenCart Store
Prepared/Modified by | Role | Date of Preparation
Bug Squashers | Tester | 2018-08-04
Reviewed by | Role | Date of Review
Swathi | Test Lead
Approved by | Role | Date of Approval
Geethika | Test Manager
Circulation List
Version Number | 1

## DEFECT TRACKING SHEET
Project ID: Prj_Opencart_001 |  | Project Name: OpenCart Store
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
OC_01 | First_Name | The First name is accepting all special and numerical characters | Detailed Description: The first name is accepting all the characters Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Click on account information 5. The user enter all the valid cerdentails Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user first name is accepting all the special and numerical characters | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-08-04 | bhavya | Jahnavi | ACTIVE | Test Cycle 1 | TC_FN-04 | [6 empty] | FirstNameDefect.JPG
OC_02 | Last_Name | The Last name is accepting all special and numerical characters | Detailed Description: The last name is accepting all the characters Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Click on account information 5. The user enter all the valid cerdentails Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user last name is accepting all the special and numerical characters | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-08-04 | bhavya | Jahnavi | ACTIVE | Test Cycle 1 | TC_LN_04 | [6 empty] | LastNameDefect.JPG
OC_03 | Telephone_no | The Telephone is accepting alphabets characters | Detailed Description: The telephone number is accepting alphabets Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login 4. Click on account information 5. The user enter all the valid cerdentails Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user telephone number is accepting alphabets | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-08-04 | bhavya | Jahnavi |  | Test Cycle 1 | TC_TN_04 | [6 empty] | MobileNumDefect.JPG